## Model_Completion_time
Main Model
Office LAN project - finding project time and critical path
Data on activity network
Activity | Label | Predecessors | Successors | Duration
Start | Start | None | A | 0
Perform needs analysis | A | Start | B | 10
Develop specifications | B | A | C,D | 6
Select server | C | B | E,G | 6
Select software | D | B | F,G | 12
Select cables | E | C | F | 4
Purchase equipment | F | D,E | H,I | 3
Develop user manuals | G | C,D | J | 6
Wire offices | H | F | L | 12
Set up server | I | F | K | 3
Develop training program | J | G | M | 14
Install software | K | I | L | 4
Connect network | L | H,K | M,N | 3
Train users | M | J,L | O | 8
Test & debug system | N | L | O | 12
Get management acceptance | O | M,N | Finish | 4
Finish | Finish | O | None | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest start time | Latest finish time | Slack
Start | 0 | 0 | 0 | 0
A | 0 | 10 | 0 | 10 | 0
B | 10 | 16 | 10 | 16 | 0
C | 16 | 22 | 18 | 24 | 2
D | 16 | 28 | 16 | 28 | 0
E | 22 | 26 | 24 | 28 | 2
F | 28 | 31 | 28 | 31 | 0
G | 28 | 34 | 30 | 36 | 2
H | 31 | 43 | 31 | 43 | 0
I | 31 | 34 | 36 | 39 | 5
J | 34 | 48 | 36 | 50 | 2
K | 34 | 38 | 39 | 43 | 5
L | 43 | 46 | 43 | 46 | 0
M | 48 | 56 | 50 | 58 | 2
N | 46 | 58 | 46 | 58 | 0
O | 58 | 62 | 58 | 62 | 0
Finish | 62 | 62 | 62 | 62
Project completion time | 62
Note on B27: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C27: Earliest start time plus duration
Note on D27: Latest finish time minus duration
Note on E27: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on F27: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time
Note on BL74: Mughal, Tariq: This is how much we can save if we use LST for activities which have slack.

## Gantt Chart
Activity | Start Time | Duration
Perform needs analysis | 0 | 10
Develop specifications | 10 | 6
Select server | 16 | 6
Select software | 16 | 12
Select cables | 22 | 4
Purchase equipment | 28 | 3
Develop user manuals | 28 | 6
Wire offices | 31 | 12
Set up server | 31 | 3
Develop training program | 34 | 14
Install software | 34 | 4
Connect network | 43 | 3
Train users | 48 | 8
Test & debug system | 46 | 12
Get management acceptance | 58 | 4
Note on BL29: Mughal, Tariq: This is how much we can save if we use LST for activities which have slack.

## Model_w_oneway_n_two_way_Tables
Main Model
Comp Times with with varying times for activity B (column) and Activity E (Rows)
[8 empty] | 62 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Office LAN project - finding project time and critical path | [7 empty] | 4 | 60 | 60 | 60 | 60 | 60 | 61 | 62 | 63
Data on activity network | [5 empty] | One way Table |  | 5 | 61 | 61 | 61 | 61 | 61 | 62 | 63 | 64
[8 empty] | 6 | 62 | 62 | 62 | 62 | 62 | 63 | 64 | 65
Activity | Label | Predecessors | Successors | Duration |  | Activity B Duration | 62 | 7 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 66
Start | Start | None | A | 0 |  | 4 | 60 | 8 | 64 | 64 | 64 | 64 | 64 | 65 | 66 | 67
Perform needs analysis | A | Start | B | 10 |  | 5 | 61 | 9 | 65 | 65 | 65 | 65 | 65 | 66 | 67 | 68
Develop specifications | B | A | C,D | 6 |  | 6 | 62 | 10 | 66 | 66 | 66 | 66 | 66 | 67 | 68 | 69
Select server | C | B | E,G | 6 |  | 7 | 63 | 11 | 67 | 67 | 67 | 67 | 67 | 68 | 69 | 70
Select software | D | B | F,G | 12 |  | 8 | 64 | 12 | 68 | 68 | 68 | 68 | 68 | 69 | 70 | 71
Select cables | E | C | F | 4 |  | 9 | 65 | 13 | 69 | 69 | 69 | 69 | 69 | 70 | 71 | 72
Purchase equipment | F | D,E | H,I | 3 |  | 10 | 66
Develop user manuals | G | C,D | J | 6 |  | 11 | 67
Wire offices | H | F | L | 12 |  | 12 | 68
Set up server | I | F | K | 3 |  | 13 | 69
Develop training program | J | G | M | 14
Install software | K | I | L | 4
Connect network | L | H,K | M,N | 3
Train users | M | J,L | O | 8
Test & debug system | N | L | O | 12
Get management acceptance | O | M,N | Finish | 4
Finish | Finish | O | None | 0
Activity start and finish times
Activity | Earliest start time | Earliest finish time | Latest start time | Latest finish time | Slack
Start | 0 | 0 | 0 | 0
A | 0 | 10 | 0 | 10 | 0
B | 10 | 16 | 10 | 16 | 0
C | 16 | 22 | 18 | 24 | 2
D | 16 | 28 | 16 | 28 | 0
E | 22 | 26 | 24 | 28 | 2
F | 28 | 31 | 28 | 31 | 0
G | 28 | 34 | 30 | 36 | 2
H | 31 | 43 | 31 | 43 | 0
I | 31 | 34 | 36 | 39 | 5
J | 34 | 48 | 36 | 50 | 2
K | 34 | 38 | 39 | 43 | 5
L | 43 | 46 | 43 | 46 | 0
M | 48 | 56 | 50 | 58 | 2
N | 46 | 58 | 46 | 58 | 0
O | 58 | 62 | 58 | 62 | 0
Finish | 62 | 62 | 62 | 62
Project completion time | 62
Note on B28: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on C28: Earliest start time plus duration
Note on D28: Latest finish time minus duration
Note on E28: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on F28: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time
Note on BL75: Mughal, Tariq: This is how much we can save if we use LST for activities which have slack.

## Model_W_Crashing
Main Model | Please note: Using the Evolutionary Solver Algorithm, you may get a different answer.
Office LAN project - finding project time and critical path
Data on activity network
Activity |  | Label | Predecessors | Successors | Duration
Start |  | Start | None | A | 0 |  | Original Duration | Reduction | < = | Max Reduction | Cost per day
Perform needs analysis |  | A | Start | B | 10 |  | 10 | 0 | < = | 2 | 600
Develop specifications |  | B | A | C,D | 5 |  | 6 | 1 | < = | 1 | 600
Select server |  | C | B | E,G | 6 |  | 6 | 0 | < = | 1 | 480
Select software |  | D | B | F,G | 10 |  | 12 | 2 | < = | 3 | 480
Select cables |  | E | C | F | 4 |  | 4 | 0 | < = | 1 | 480
Purchase equipment |  | F | D,E | H,I | 3 |  | 3 | 0 | < = | 0
Develop user manuals |  | G | C,D | J | 6 |  | 6 | 0 | < = | 1 | 360
Wire offices |  | H | F | L | 12 |  | 12 | 0 | < = | 4 | 540
Set up server |  | I | F | K | 3 |  | 3 | 0 | < = | 0
Develop training program |  | J | G | M | 14 |  | 14 | 0 | < = | 4 | 360
Install software |  | K | I | L | 4 |  | 4 | 0 | < = | 1 | 480
Connect network |  | L | H,K | M,N | 3 |  | 3 | 0 | < = | 0
Train users |  | M | J,L | O | 8 |  | 8 | 0 | < = | 2 | 360
Test & debug system |  | N | L | O | 10 |  | 12 | 2 | < = | 3 | 480
Get management acceptance |  | O | M,N | Finish | 3 |  | 4 | 1 | < = | 1 | 300
Finish |  | Finish | O | None | 0
Activity start and finish times | [6 empty] | Crashing Cost | 2820
Activity |  | Earliest start time | Earliest finish time | Latest start time | Latest finish time | Slack | Penalty | 0
Start |  | 0 | 0 | 0 | 0 |  | Total Crashing Cost | 2820
A |  | 0 | 10 | 0 | 10 | 0
B |  | 10 | 15 | 10 | 15 | 0
C |  | 15 | 21 | 15 | 21 | 0
D |  | 15 | 25 | 15 | 25 | 0
E |  | 21 | 25 | 21 | 25 | 0
F |  | 25 | 28 | 25 | 28 | 0
G |  | 25 | 31 | 25 | 31 | 0
H |  | 28 | 40 | 28 | 40 | 0
I |  | 28 | 31 | 33 | 36 | 5
J |  | 31 | 45 | 31 | 45 | 0
K |  | 31 | 35 | 36 | 40 | 5
L |  | 40 | 43 | 40 | 43 | 0
M |  | 45 | 53 | 45 | 53 | 0
N |  | 43 | 53 | 43 | 53 | 0
O |  | 53 | 56 | 53 | 56 | 0
Finish |  | 56 | 56 | 56 | 56
| Project completion time | 56 |  | Dead Line | 56
Note on F6: Mughal, Tariq: Original Duration minus reduction
Note on C27: 0 for Start node, for all others is equal to maximum earliest finish time, where maximum is over all predecessors
Note on D27: Earliest start time plus duration
Note on E27: Latest finish time minus duration
Note on F27: Equal to project time for Finish node; for others, equal to minimum of latest start times, where minimum is over all successors
Note on G27: Latest start time minus earliest start time. Equivalently, latest finish time minus earliest finish time
Note on I28: Mughal, Tariq: This is the objective function