## Model
Office LAN project - finding project time and critical path
Data on activity network
Activity | Label | Predecessors | Successors | Duration
START | START | NONE | A | 0
Perform needs analysis | A | Start | B | 10
Develop specifications | B | A | C,D | 6
Select server | C | B | E,G | 6
Select software | D | B | F,G | 12
Select cables | E | C | F | 4
Purchase equipment | F | D,E | H,I | 3
Develop user manuals | G | C,D | J | 6
Wire offices | H | F | L | 12
Set up server | I | F | K | 3
Develop training program | J | G | M | 14
Install software | K | I | L | 4
Connect network | L | H,K | M,N | 3
Train users | M | J,L | O | 8
Test & debug system | N | L | O | 12
Get management acceptance | O | M,N | Finish | 4
FINISH | FINISH | O | NONE | 0
Activity start and finish times
Activity | ES | EF | LS | LF | Slack | Date EF
Start | 0 | 0
A | 0 | 10
B | 10 | 16
C |  | 6
D |  | 12
E |  | 4
F |  | 3
G |  | 6
H |  | 12
I |  | 3
J |  | 14
K |  | 4
L |  | 3
M |  | 8
N |  | 12
O |  | 4
Finish |  | 0
Project completion time
Note on B24: Mughal, Tariq: Zero for Start Node. For all others, max Earliest Finish time, where max is over all Predecessors.
Note on C24: Earliest Start Time + Duration
Note on D24: Latest Finish time minus durations
Note on E24: Mughal, Tariq: Here we start at the bottom: For the finish Node: Equal the project finish time. For all others, min of Latest Start times, where min is over all successors.
Note on F24: Latest finish - earliest finsh. Activities with zero slack implies critical
Note on G24: Mughal, Tariq: How would we find the actual calender date of Earliest finish if we worked every day